## Feature Tracker
Knowledge Ingestion, RAG and Knowledge Graph Feature Tracker
Forty main features covering knowledge ingestion, cataloging, vector and BM25 retrieval, knowledge-graph creation, hybrid ranking, grounding, governance, and release.
Features | Change (Short Description) | Status | Notes About What Is Required or Blockers
Define the knowledge-platform scope and supported business questions | Establish the documents, structured data, entities, relationships, and question types that the first release will support. | Not Started | Requires an approved pilot process, in-scope use cases, explicit exclusions, and accountable business and technical owners.
Create a complete inventory of knowledge and process-data sources | Catalogue document repositories, APIs, databases, search indexes, process models, metadata stores, and their update patterns. | Not Started | Requires source owners, locations, formats, volumes, refresh frequency, security classification, and access method for each source.
Build a governed source-registration and configuration service | Maintain source identity, owner, tenant, process mapping, connection configuration, schedule, status, and credential reference. | Not Started | Blocked until the canonical source schema and approved secrets-management method are defined.
Develop connectors for documents, APIs, metadata, and process models | Retrieve supported files, API records, structured metadata, and BPMN or other process-model definitions from approved systems. | Not Started | Requires credentials, network routes, API pagination rules, rate limits, supported formats, and representative source samples.
Detect new, changed, unchanged, and deleted source content | Compare source identifiers, timestamps, checksums, and versions to determine the correct incremental-ingestion action. | Not Started | Requires stable source identities, reliable change indicators, delete detection, and rules for forced reprocessing.
Preserve original source content in an immutable raw landing area | Store the original source bytes and ingestion metadata before parsing, normalization, or enrichment begins. | Not Started | Requires encrypted storage, tenant isolation, retention rules, checksums, ingestion IDs, and access-control snapshots.
Parse supported business documents into structured canonical content | Extract headings, paragraphs, lists, links, tables, pages, slides, notes, and source coordinates from supported formats. | Not Started | Requires an approved format list, parser selection, representative test documents, and minimum extraction-quality thresholds.
Add OCR and language handling for scanned or mixed-language documents | Apply OCR when digital text is unavailable and detect the document or section language for later processing. | Not Started | Requires an approved OCR engine, language coverage, confidence thresholds, and a process for reviewing low-confidence pages.
Extract tables and process-model structures without losing relationships | Preserve table headers and rows and extract BPMN activities, events, gateways, lanes, systems, and sequence flows. | Not Started | Requires table-splitting rules, BPMN element-ID preservation, supported notation, and validation for dangling model references.
Normalize extracted content while preserving business meaning | Standardize Unicode, whitespace, line breaks, repeated headers, footers, boilerplate, and other parser inconsistencies. | Not Started | Requires deterministic normalization rules and tests proving that unique policy, process, and table content is not removed.
Create a canonical document model for every supported source format | Represent pages, sections, paragraphs, tables, images, links, slides, and process-model elements in one versioned schema. | Not Started | Requires stable element IDs and source-location fields that can later support citations and audit tracing.
Implement content-aware parent and child chunk generation | Create section-aware, semantic, table-aware, and process-model-aware chunks with parent-child relationships. | Not Started | Requires target and maximum token sizes, overlap rules, content-type policies, and handling for unusually large tables or sections.
Enrich every chunk with business, technical, and governance metadata | Attach tenant, process, hierarchy, entity type, owner, source, version, effective date, classification, and permission metadata. | Not Started | Blocked until canonical metadata fields, source-to-canonical mappings, inheritance rules, and mandatory fields are approved.
Generate stable identities for documents, elements, and chunks | Create deterministic IDs that remain stable for unchanged content and change predictably when content or policies change. | Not Started | Requires an agreed identity formula using tenant, source, version, structural path, policy version, and content fingerprint.
Maintain end-to-end lineage from source content to every derived record | Trace catalog records, chunks, embeddings, lexical records, graph facts, and responses back to the originating source and ingestion run. | Not Started | Requires consistent correlation IDs, source versions, parser versions, chunk-policy versions, index versions, and publication versions.
Build the canonical knowledge catalog for process-related entities | Store governed processes, subprocesses, activities, systems, risks, controls, policies, documents, owners, and lifecycle information. | Not Started | Requires authoritative-source decisions, canonical identifiers, entity schemas, ownership, effective dates, and version rules.
Represent process hierarchy and cross-entity mappings explicitly | Maintain root processes, subprocesses, hierarchy levels, activity membership, system usage, policy applicability, and risk-control mappings. | Not Started | Requires validated parent-child rules, cycle prevention, orphan detection, and agreement on how hierarchy changes are versioned.
Create an approved alias, synonym, and business terminology registry | Map business names, abbreviations, technical IDs, common misspellings, and alternate terms to canonical entities. | Not Started | Requires process-scoped alias rules, collision detection, ambiguity handling, provenance, approval status, and language support.
Package and publish versioned knowledge configuration by process | Bundle entity metadata, hierarchy, aliases, mappings, retrieval settings, security rules, and compatible versions for each process. | Not Started | Requires manifest validation, atomic publication, compatibility checks, promotion approval, and rollback support.
Select and govern the embedding model used for semantic retrieval | Evaluate embedding quality, supported languages, context limits, vector dimensions, latency, cost, privacy, and deployment constraints. | Not Started | Blocked until representative documents and retrieval queries are available for benchmarking and acceptance thresholds are approved.
Generate embeddings through a reliable and traceable batch process | Create queryable vectors for eligible chunks and entities while recording the model, tokenizer, token count, checksum, and processing status. | Not Started | Requires batch-size limits, bounded retries, partial-failure handling, sensitive-content rules, and dimension validation.
Manage vector-index insertion, update, deletion, promotion, and rollback | Upsert vectors idempotently, remove stale or revoked records, validate index integrity, and switch active index versions safely. | Not Started | Requires stable chunk IDs, optimistic version checks, metadata filters, count reconciliation, index aliases, and revocation SLAs.
Build a BM25 lexical index for exact terms, names, and technical IDs | Index body text, titles, headings, entity names, aliases, phrases, and exact identifiers using language-aware analyzers. | Not Started | Requires versioned mappings, analyzers, stopwords, synonyms, keyword fields, identifier preservation, and field-boost configuration.
Define the knowledge-graph ontology and approved business relationships | Specify node types, relationship types, direction, allowed endpoints, properties, provenance, temporal meaning, and graph use cases. | Not Started | Requires business approval for dependency, ownership, containment, usage, governance, mitigation, applicability, and impact semantics.
Extract candidate business entities from documents and process models | Identify processes, activities, systems, risks, controls, policies, documents, owners, business units, markets, and data objects. | Not Started | Requires labelled examples, evidence-span capture, entity-type rules, confidence scores, and extraction-model or rule versioning.
Extract evidence-backed relationships between business entities | Identify dependencies, ownership, system usage, process containment, policy applicability, control mitigation, and related graph facts. | Not Started | Requires approved predicates, correct direction, negation and uncertainty handling, evidence references, and confidence thresholds.
Resolve extracted and user-mentioned entities to canonical identities | Apply exact ID, exact name, approved alias, lexical, and semantic matching within the correct tenant and process scope. | Not Started | Requires match precedence, ambiguity thresholds, canonical catalog APIs, out-of-scope rejection, and explicit clarification behavior.
Provide human review for ambiguous or high-impact graph facts | Allow knowledge stewards to approve, reject, correct, dispute, or retire uncertain entities and relationships. | Not Started | Requires reviewer roles, queues, evidence display, state transitions, decision audit, review SLAs, and escalation for unresolved conflicts.
Insert and update graph nodes and relationships safely and idempotently | Persist canonical nodes and evidence-backed edges using graph constraints, version checks, idempotency keys, and atomic source-version writes. | Not Started | Requires graph keys, uniqueness constraints, endpoint validation, provenance, transaction boundaries, and handling for stale concurrent writes.
Version, retire, revoke, reconcile, and roll back graph knowledge | Maintain current and historical facts, remove unauthorized evidence, reconcile expected records, and control active graph publications. | Not Started | Requires effective-date semantics, supersession rules, multi-source evidence behavior, active-version pointers, and rollback verification.
Orchestrate the complete knowledge-ingestion pipeline with checkpoints | Coordinate landing, parsing, normalization, chunking, enrichment, embeddings, lexical indexing, graph creation, validation, and publication. | Not Started | Requires a stage state machine, durable checkpoints, bounded retries, dead-letter handling, replay, cancellation, and dependency management.
Enforce cross-store quality gates before knowledge becomes searchable | Validate source governance, parser quality, chunk coverage, catalog integrity, vector and lexical counts, graph constraints, and freshness. | Not Started | Requires versioned quality rules, blocking thresholds, readiness reports, exception approval, and one cross-store publication barrier.
Expose governed APIs for knowledge insertion, update, deletion, and reprocessing | Provide controlled operations for source ingestion, catalog upsert, document correction, revocation, reprocessing, publication, and rollback. | Not Started | Requires authorization, schema validation, idempotency, batch limits, optimistic concurrency, dry-run impact, and a typed error taxonomy.
Understand user intent, process context, entities, filters, and ambiguity | Interpret the requested knowledge operation and resolve process, entity, document type, hierarchy, status, date, and graph-traversal requirements. | Not Started | Requires a supported-intent catalog, canonical entity resolution, parameter-source tracking, confidence thresholds, and focused clarifications.
Apply mandatory scope and authorization filters before every retrieval | Restrict retrieval by tenant, process, hierarchy, permissions, classification, status, effective date, entity type, and document type. | Not Started | Blocked until the authorization model and filterable metadata fields are implemented consistently in every retrieval store.
Retrieve candidates through exact, lexical, vector, metadata, and graph channels | Use the most appropriate retrieval channels for technical identifiers, keywords, semantic concepts, structured filters, and multi-hop relationships. | Not Started | Requires a common result contract, per-channel top-K limits, timeout budgets, fallback rules, stable versions, and evidence references.
Fuse and deduplicate candidates from all retrieval channels | Canonicalize candidate identities, remove duplicate or overlapping evidence, and combine ranked lists using configurable reciprocal-rank fusion. | Not Started | Requires channel eligibility rules, pool limits, RRF parameters, deterministic ties, score diagnostics, and preservation of channel contributions.
Rerank retrieved evidence and determine whether the question is answerable | Apply relevance models and governed features, diversify evidence, enforce thresholds, and classify results as answer, clarify, partial, or no-answer. | Not Started | Requires a bounded reranking pool, model and weight versions, timeout fallback, confidence calibration, conflict handling, and evaluation targets.
Assemble grounded evidence with citations and graph-path explanations | Build a token-bounded evidence package containing ranked chunks, parent context, graph paths, conflicts, canonical facts, and stable source citations. | Not Started | Requires source-location resolution, token-budget rules, claim-to-evidence validation, citation security checks, and prevention of unsupported graph inferences.
Operate the platform securely and release the pilot through measurable gates | Enforce isolation, redaction, prompt-injection protection, audit, retention, deletion, monitoring, evaluation, runbooks, UAT, and controlled rollout. | Not Started | Requires security approval, golden datasets, quality and performance thresholds, SLOs, dashboards, incident recovery, pilot owners, and release sign-off.